## Agile Project Plan
PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
Product Release | Zae Saeed | 2019-03-15 | 2019-05-02 |  | 20% |  | SCOPE STATEMENT
TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
Sprint 1 |  |  |  | 2019-03-16 | 2019-03-31 | 15
Feature 1 | Platform Setup | Dylan, Gilbert | 1,2 | 2019-03-16 | 2019-03-23 | 5 | Not Started | Set up platforms/environments
Feature 2 | Project Layout | Shahzada S. | 2,3,4 | 2019-03-23 | 2019-03-27 | 5 | Not Started | Design/brainstorm project layout
Feature 3 | User Login Form | Jake Loff | 6,7 | 2019-03-27 | 2019-03-31 | 5 | Not Started | Start implementation
Sprint 2 |  |  |  | 2019-04-01 | 2019-04-11 | 10 | Not Started
Feature 4 | User Creation | Zae S. | 7,8 | 2019-04-01 | 2019-04-04 | 3 | Not Started | implement adminstrater features
Feature 5 | User Input Validation | Geo Q. | 9 | 2019-04-04 | 2019-04-07 | 3 | Not Started | Implement user features
Feature 6 | Admin. Test Bank Development | Victor C. | 2,3 | 2019-04-07 | 2019-04-11 | 4 | Not Started | analysis/testing
Team Members: Zae Saeed, Dylan Davidson, Gilbert Alvarado, Jacob Loff, Geovanny Quiroz, Shahzada Shah, Victor Compres